## Current Full Programme
Calander | 2021 |  |  |  | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026
| sept | oct | nov | dec | jan | feb | mar | april | may | june | july | aug | sept | oct | nov | dec | jan | feb | mar | april | may | june | july | aug | sept | oct | nov | dec | jan | feb | mar | april | may | june | july | aug | sept | oct | nov | dec | jan | feb | mar | april | may | june | july | aug | sept | oct | nov | dec | jan | feb | mar | april | may | june | july | aug | sept | oct | nov | dec
Financial Year | 2021 sept: 2021/22 FY; 2022 april: 2022/2023; 2023 april: 2023/2024; 2024 april: 2024/2025; 2025 april: 2025/2026; 2026 april: 2026/27
Workstreams • Milestones
Negoitations 13 + 15 Castle Hill
Conveyencing 13+ 15 Castle Hill
Negoiations zoo lease purchase and/or land swap
Conveyencing zoo lease
TF Stage 2 full business case development
• TF Stage 2 Cabinet report 15/12/2021
• TF Stage 2 Business Case submitted 14/01/2022
• TF Stage 2 Outcome
Contract provider procurement
•Contract provider appointed
Stage One: Tender, Evaluation and Partner selection
• Alliance agreement signed
Stage Two: Detailed design and cost consulting
|  |  | DMBC Planning committee 17/11/21 | [13 empty] | • Detailed design agreed
• Call in decision issued. Not called in
• DMBC Grants planning approval
• Planning conditions discharged
Demolition and remediation contractor procurement
•Demolition contractor appointed
Asbestos and remediation
Demolition
• Site Cleared
On-site main building works
• Practical Completion
Fit out and commissioning
• HEI Operational
Key | 2025 may: Payment; 2025 aug: Payment
[45 empty] | ? |  |  | ?
TF Funding | bar: 2021 sept
Site Acquisition | bar: 2021 sept
Insurance-backed alliancing construction contract | bar: 2021 sept
Demolition and remediaiton | bar: 2021 sept
Land Assembly | bar: 2021 sept
Planning | bar: 2021 sept
Main Building works | bar: 2021 sept

## Programme indicative if CPO
Calander | 2021 |  |  |  | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026
| sept | oct | nov | dec | jan | feb | mar | april | may | june | july | aug | sept | oct | nov | dec | jan | feb | mar | april | may | june | july | aug | sept | oct | nov | dec | jan | feb | mar | april | may | june | july | aug | sept | oct | nov | dec | jan | feb | mar | april | may | june | july | aug | sept | oct | nov | dec | jan | feb | mar | april | may | june | july | aug | sept | oct | nov | dec
Financial Year | 2021 sept: 2021/22 FY; 2022 april: 2022/2023; 2023 april: 2023/2024; 2024 april: 2024/2025; 2025 april: 2025/2026; 2026 april: 2026/27
Workstreams • Milestones | 2021 sept: Negoiations zoo lease purchase and/or land swap
Conveyencing zoo lease
CPO 15 Castle Hill prepartion
• Cabinet report formulating CPO powers
Inquiry
• Site Acquired
TF Stage 2 full business case development
• TF Stage 2 Cabinet report 15/12/2021
• TF Stage 2 Business Case submitted 14/01/2022
• TF Stage 2 Outcome
Contract provider procurement
•Contract provider appointed
Stage one: IPI Tender, Evaluation and Partner selection
• Alliance agreement signed
Stage Two: Detailed design and cost negoitations
|  |  | DMBC Planning committee 17/11/21 | [16 empty] | • Detailed design agreed
• Call in decision issued. Not called in
• DMBC Grants planning approval
• Planning conditions discharged
Demolition and remediation contractor procurement
•Demolition contractor appointed
Asbestos and remediation
Demolition
• Site Cleared
On-site main building works
• Practical Completion
Fit out and commissioning
• HEI Operational
Key
TF Funding | bar: 2021 sept
Site Acquisition | bar: 2021 sept
Insurance-backed alliancing construction contract | bar: 2021 sept
Demolition and remediaiton | bar: 2021 sept
Land Assembly | bar: 2021 sept
Planning | bar: 2021 sept
Main Building works | bar: 2021 sept